## Sheet1
Project Name | PROPOSED CUEA HOSTELS FOR SPRUCE PROPERTIES LLP (PHASE 1)
Project Number | SK/20/2519
Project Stage | STAGE 5 -PRODUCTION INFORMATION
Date | 2021-12-03
Role | Company | Role
Client | SPRUCE PROPERTIES LLP | M & E | GDEA
Project Manager | ACORN | QS | BBK
Architect | SYMBION
Structural Engineer | GATH
Deliverables Schedule (Qejani Double and Quad)
Sheet Number | Drawing Title | Paper size | Scale | STATUS |  |  |  | Resource
0000-999 | GENERAL |  |  |  | Duration | Start Date | End date
CUEA-SK-ZZ-00-A-0011 | Phase 1 and 2 Site Plan | A0 | 1:500 | Done |  |  |  | CA
CUEA-SK-ZZ-00-A-0012 | Proposed site plan -Zoned | A1 | 1:200 | Done |  |  |  | CA
CUEA-SK-ZZ-00-A-0013 | Site setting out plan | A1 | 1:200 | Done |  |  |  | CA
1100 | SETTING OUT
CUEA-SK-2.4-00-A-1101 | Ground & First Floor plan | A1 | 1:100 | Done |  |  |  | LN
CUEA-SK-2.1-XX-A-1102 | Typical & Fourth Floor Plan | A1 | 1:100 | Done |  |  |  | LN
CUEA-SK-2.1-05-A-1103 | Roof Terrace & Upper Roof Plan | A1 | 1:100 | Done |  |  |  | LN
1300 | OPENINGS LAYOUTS
CUEA-SK-2.4-00-A-1301 | Ground & First Floor | A1 | 1:100 | Done |  |  |  | LN
CUEA-SK-2.1-XX-A-1302 | Typical & Fourth Floor Plan | A1 | 1:100 | Done |  |  |  | LN
CUEA-SK-2.1-0 5-A-1303 | Roof Terrace | A1 | 1:100 | Done |  |  |  | LN
1400 | FINISHES LAYOUTS
CUEA-SK-2.4-00-A-1401 | Ground & First Floor | A1 | 1:100 | Partial |  | 21/07/2021 | 21/07/2021 | LN
CUEA-SK-2.1-XX-A-1402 | Typical & Fourth Floor | A1 | 1:100 | Partial |  | 21/07/2021 | 21/07/2021 | LN
CUEA-SK-2.1-05-A-1403 | Roof Terrace | A1 | 1:100 | Partial |  | 21/07/2021 | 21/07/2021 | LN
2000 | SECTIONS AND ELEVATIONS
CUEA-SK-02-XX-A-2001 | Section 2001 & 2002 | A1 | 1:100 | Done | 1 day |  |  | LN
CUEA-SK-02-XX-A-2002 | Elevation 2003 & 2004 | A1 | 1:100 | Done |  |  |  | LN
CUEA-SK-02-XX-A-2003 | Elevation 2005 & 2006 | A1 | 1:100 | Done |  |  |  | LN
3000 | BLOWUPS
CUEA-SK-2.1-XX-A-3001 | Double Room | A1 | 1:20 | Pending | 1 day | 23/7/2021 | 23/7/2031 | LN
CUEA-SK-2.1-XX-A-3002 | Kitchenette Room | A1 | 1:20 | Pending |  |  |  | LN
|  |  |  | Pending |  |  |  | LN
CUEA-SK-02-XX-A-34400 | Staircase 01 Blow up | A1 | 1:20 | Done |  |  |  | LN
CUEA-SK-02-XX-A-34401 | Staircase 02 Blow up | A1 | 1:20 | Done |  |  |  | LN
CUEA-SK-02-XX-A-34402 | Ramp Blow up | A1 | 1:20 | Pending |  |  |  | LN
CUEA-SK-02-XX-A-34403 | Steps Blow up | A1 | 1:20 | Pending |  |  |  | LN
|  |  |  | Pending |  |  |  | LN
CUEA-SK-2.1-XX-A-37100 | Residents Washrooms | A3 | 1:20 | Pending |  |  |  | LN
CUEA-SK-2.1-XX-A-37101 | Laundry Area | A3 | 1:20 | Pending |  |  |  | LN
42100 | EXTERNAL WALL SCHEDULES
CUEA-SK-ZZ-XX-A-42100 | 200mm Thick Masonry Wall | A4 | 1:5 | Pending | 1/2 day | 26/7/2021 | 26/4/2021 | LN
CUEA-SK-ZZ-XX-A-42101 | 250mm Thick RC Wall | A4 | 1:5 | Pending |  |  |  | LN
CUEA-SK-ZZ-XX-A-42102 | 150mm Thick Masonry Wall | A4 | 1:5 | Pending |  |  |  | LN
CUEA-SK-ZZ-XX-A-42103 | 100mm Thick Masonry Wall | A4 | 1:5 | Pending |  |  |  | LN
43000 | DOOR & WINDOW SCHEDULES
CUEA-SK-2.1-XX-S-43000 | Door Schedules | A3 | 1:20 | Partial | 1/2 day | 26/7/2021 | 26/7/2021 | LN
CUEA-SK-2.1-XX-S-43010 | Window Schedules | A3 | 1:20 | Done |  |  |  | LN
CUEA-SK-XX-XX-S-43050 | Iron Mongery schedule | A4 | NTS | Done |  |  |  | CA
44000 | FINISHES SCHEDULES
CUEA-SK-ZZ-XX-S-44000 | Finishes and Specifications schedules | A4 | NTS | Pending | 1 day | 27/7/2021 | 27/7/2021 | CA
45000 | SANITARY SCHEDULES
CUEA-SK-ZZ-XX-S-45000 | Sanitary and accessories schedules | A1 | 1:100 | Partial | 1 day | 27/7/2021 | 27/7/2021 | CA
52100 | EXTERNAL WALL DETAILS
CUEA-SK-2.1-XX-A-52100 | External wall details | A3 | 1:10 | Pending | 1/2 day | 27/7/2021 | 27/7/2021 | LN
CUEA-SK-2.1-XX-A-52101 | Internal wall details | A3 | 1:10 | Pending |  |  |  | LN
52700 | ROOF DETAILS
CUEA-SK-02-06-A-52700 | Roof Details | A3 | 1:10 | Pending | 1/2 day |  |  | LN
CUEA-SK-02-01-A-52701 | Canopy Details | A3 | 1:10 | Pending |  | 27/7/2021 | 27/7/2021 | LN
53200 | ASSEMBLY DETAILS
CUEA-SK-ZZ-XX-A-53200 | Window Sill, Jamb & head details | A3 | 1:5 | Pending | 1/2 day | 28/7/2021 | 28/7/2021 | LN
CUEA-SK-ZZ-XX-A-53201 | Door Jamb & head details | A3 | 1:5 | Pending |  | 28/7/2021 | 28/7/2021 | LN
53400 | HANDRAIL AND BARRIER DETAILS
CUEA-SK-ZZ-XX-A-53400 | MS Balustrade details | A3 | 1:5 | Pending | 1/2 day | 28/7/2021 | 28/7/2021 | LN
CUEA-SK-ZZ-05-A-53401 | Safety mesh details | A3 | 1:10 | Pending |  | 28/7/2021 | 28/7/2021 | LN
CUEA-SK-ZZ-00-A-53402 | Palisade Fence Details | A3 | 1:10 | Pending |  | 28/7/2021 | 28/7/2021 | LN
54100 | EXTERNAL WALL FINISHES DETAILS
CUEA-SK-ZZ-XX-A-54100 | Coping Details | A3 | 1:5 | Pending | 1/4 day | 29/7/2021 | 29/7/2021 | LN
54200 | INTERNAL WALL FINISHES DETAILS
CUEA-SK-ZZ-XX-A-54200 | Skirting details MDF and Tile | A3 | 1:5 | Pending | 1/4 day | 29/7/2021 | 29/7/2021 | LN
54300 | INTERNAL FLOOR FINISHES DETAILS
CUEA-SK-ZZ-00-A-54301 | Mattwell detail | A3 | 1:5 | Pending | 1/4 day | 29/7/2021 | 29/7/2021 | LN
CUEA-SK-ZZ-XX-A-54302 | Door threshold details | A3 | 1:5 | Pending |  | 29/7/2021 | 29/7/2021 | LN
54400 | STAIRCASE AND RAMP DETAILS
CUEA-SK-02-01-A-54401 | MS Railing Details | A3 | 1:5 | Pending | 1/4 day | 29/7/2021 | 29/7/2021 | LN
CUEA-SK-02-01-A-54401 | Step Details | A3 | 1:5 | Pending |  | 29/7/2021 | 29/7/2021 | LN
54500 | CEILING DETAILS
CUEA-SK-ZZ-01-A-54501 | Ceiling Details | A1 | 1:100 | Pending | 1/4 day | 30/7/2021 | 30/7/2021 | LN
57100 | SIGNS/PINBOARDS
CUEA-SK-ZZ-XX-A-57100 | Site Sign board | A1 | 1:100 | Done |  |  |  | GO
57200 | FITTINGS DETAILS
CUEA-SK-02-XX-A-57201 | Kitchenette Counter details | A4 | NTS | Pending | 1/2 day | 30/7/2021 | 30/7/2021 | LN
CUEA-SK-ZZ-06-A-57202 | Dhobi sink countertop details | A4 | NTS | Pending |  |  |  | LN
57300 | SANITARY FITTINGS DETAILS
CUEA-SK-ZZ-XX-A-57300 | Vanity Top Details | A1 | 1:100 | Pending | 1/4 day | 30/7/2021 | 30/7/2021 | LN
|  | KEY | PENDING
PARTIAL
DONE

## Sheet2
Project Name | PROPOSED CUEA HOSTELS FOR SPRUCE PROPERTIES LLP (PHASE 1)
Project Number | SK/20/2519
Project Stage | STAGE 5 -PRODUCTION INFORMATION
Date | 2021-12-03
Role | Company | Role
Client | SPRUCE PROPERTIES LLP | M & E | GDEA
Project Manager | ACORN | QS | BBK
Architect | SYMBION
Structural Engineer | GATH
Deliverables Schedule (Qejani Double and Quad)
Sheet Number | Drawing Title | Paper size | Scale | STATUS |  |  |  | Resource
0000-999 | GENERAL |  |  |  | Duration | Start Date | End date
CUEA-SK-ZZ-00-A-0011 | Phase 1 and 2 Site Plan | A0 | 1:500 | Done |  |  |  | CA
CUEA-SK-ZZ-00-A-0012 | Proposed site plan -Zoned | A1 | 1:200 | Done |  |  |  | CA
CUEA-SK-ZZ-00-A-0013 | Site setting out plan | A1 | 1:200 | Done |  |  |  | CA
1100 | SETTING OUT
CUEA-SK-2.4-00-A-1101 | Ground & First Floor plan | A1 | 1:100 | Done |  |  |  | LN
CUEA-SK-2.1-XX-A-1102 | Typical & Fourth Floor Plan | A1 | 1:100 | Done |  |  |  | LN
CUEA-SK-2.1-05-A-1103 | Roof Terrace & Upper Roof Plan | A1 | 1:100 | Done |  |  |  | LN
1300 | OPENINGS LAYOUTS
CUEA-SK-2.4-00-A-1301 | Ground & First Floor | A1 | 1:100 | Done |  |  |  | LN
CUEA-SK-2.1-XX-A-1302 | Typical & Fourth Floor Plan | A1 | 1:100 | Done |  |  |  | LN
CUEA-SK-2.1-0 5-A-1303 | Roof Terrace | A1 | 1:100 | Done |  |  |  | LN
1400 | FINISHES LAYOUTS
CUEA-SK-2.4-00-A-1401 | Ground & First Floor | A1 | 1:100 | Partial |  | 21/07/2021 | 21/07/2021 | LN
CUEA-SK-2.1-XX-A-1402 | Typical & Fourth Floor | A1 | 1:100 | Partial |  | 21/07/2021 | 21/07/2021 | LN
CUEA-SK-2.1-05-A-1403 | Roof Terrace | A1 | 1:100 | Partial |  | 21/07/2021 | 21/07/2021 | LN
2000 | SECTIONS AND ELEVATIONS
CUEA-SK-02-XX-A-2001 | Section 2001 & 2002 | A1 | 1:100 | Done | 1 day |  |  | LN
CUEA-SK-02-XX-A-2002 | Elevation 2003 & 2004 | A1 | 1:100 | Done |  |  |  | LN
CUEA-SK-02-XX-A-2003 | Elevation 2005 & 2006 | A1 | 1:100 | Done |  |  |  | LN
3000 | BLOWUPS
CUEA-SK-2.1-XX-A-3001 | Double Room | A1 | 1:20 | Pending | 1 day | 23/7/2021 | 23/7/2031 | LN
CUEA-SK-2.1-XX-A-3002 | Kitchenette Room | A1 | 1:20 | Pending |  |  |  | LN
|  |  |  | Pending |  |  |  | LN
CUEA-SK-02-XX-A-34400 | Staircase 01 Blow up | A1 | 1:20 | Done |  |  |  | LN
CUEA-SK-02-XX-A-34401 | Staircase 02 Blow up | A1 | 1:20 | Done |  |  |  | LN
CUEA-SK-02-XX-A-34402 | Ramp Blow up | A1 | 1:20 | Pending |  |  |  | LN
CUEA-SK-02-XX-A-34403 | Steps Blow up | A1 | 1:20 | Pending |  |  |  | LN
|  |  |  | Pending |  |  |  | LN
CUEA-SK-2.1-XX-A-37100 | Residents Washrooms | A3 | 1:20 | Pending |  |  |  | LN
CUEA-SK-2.1-XX-A-37101 | Laundry Area | A3 | 1:20 | Pending |  |  |  | LN
42100 | EXTERNAL WALL SCHEDULES
CUEA-SK-ZZ-XX-A-42100 | 200mm Thick Masonry Wall | A4 | 1:5 | Pending | 1/2 day | 26/7/2021 | 26/4/2021 | LN
CUEA-SK-ZZ-XX-A-42101 | 250mm Thick RC Wall | A4 | 1:5 | Pending |  |  |  | LN
CUEA-SK-ZZ-XX-A-42102 | 150mm Thick Masonry Wall | A4 | 1:5 | Pending |  |  |  | LN
CUEA-SK-ZZ-XX-A-42103 | 100mm Thick Masonry Wall | A4 | 1:5 | Pending |  |  |  | LN
43000 | DOOR & WINDOW SCHEDULES
CUEA-SK-2.1-XX-S-43000 | Door Schedules | A3 | 1:20 | Partial | 1/2 day | 26/7/2021 | 26/7/2021 | LN
CUEA-SK-2.1-XX-S-43010 | Window Schedules | A3 | 1:20 | Done |  |  |  | LN
CUEA-SK-XX-XX-S-43050 | Iron Mongery schedule | A4 | NTS | Done |  |  |  | CA
44000 | FINISHES SCHEDULES
CUEA-SK-ZZ-XX-S-44000 | Finishes and Specifications schedules | A4 | NTS | Pending | 1 day | 27/7/2021 | 27/7/2021 | CA
45000 | SANITARY SCHEDULES
CUEA-SK-ZZ-XX-S-45000 | Sanitary and accessories schedules | A1 | 1:100 | Partial | 1 day | 27/7/2021 | 27/7/2021 | CA
52100 | EXTERNAL WALL DETAILS
CUEA-SK-2.1-XX-A-52100 | External wall details | A3 | 1:10 | Pending | 1/2 day | 27/7/2021 | 27/7/2021 | LN
CUEA-SK-2.1-XX-A-52101 | Internal wall details | A3 | 1:10 | Pending |  |  |  | LN
52700 | ROOF DETAILS
CUEA-SK-02-06-A-52700 | Roof Details | A3 | 1:10 | Pending | 1/2 day |  |  | LN
CUEA-SK-02-01-A-52701 | Canopy Details | A3 | 1:10 | Pending |  | 27/7/2021 | 27/7/2021 | LN
53200 | ASSEMBLY DETAILS
CUEA-SK-ZZ-XX-A-53200 | Window Sill, Jamb & head details | A3 | 1:5 | Pending | 1/2 day | 28/7/2021 | 28/7/2021 | LN
CUEA-SK-ZZ-XX-A-53201 | Door Jamb & head details | A3 | 1:5 | Pending |  | 28/7/2021 | 28/7/2021 | LN
53400 | HANDRAIL AND BARRIER DETAILS
CUEA-SK-ZZ-XX-A-53400 | MS Balustrade details | A3 | 1:5 | Pending | 1/2 day | 28/7/2021 | 28/7/2021 | LN
CUEA-SK-ZZ-05-A-53401 | Safety mesh details | A3 | 1:10 | Pending |  | 28/7/2021 | 28/7/2021 | LN
CUEA-SK-ZZ-00-A-53402 | Palisade Fence Details | A3 | 1:10 | Pending |  | 28/7/2021 | 28/7/2021 | LN
54100 | EXTERNAL WALL FINISHES DETAILS
CUEA-SK-ZZ-XX-A-54100 | Coping Details | A3 | 1:5 | Pending | 1/4 day | 29/7/2021 | 29/7/2021 | LN
54200 | INTERNAL WALL FINISHES DETAILS
CUEA-SK-ZZ-XX-A-54200 | Skirting details MDF and Tile | A3 | 1:5 | Pending | 1/4 day | 29/7/2021 | 29/7/2021 | LN
54300 | INTERNAL FLOOR FINISHES DETAILS
CUEA-SK-ZZ-00-A-54301 | Mattwell detail | A3 | 1:5 | Pending | 1/4 day | 29/7/2021 | 29/7/2021 | LN
CUEA-SK-ZZ-XX-A-54302 | Door threshold details | A3 | 1:5 | Pending |  | 29/7/2021 | 29/7/2021 | LN
54400 | STAIRCASE AND RAMP DETAILS
CUEA-SK-02-01-A-54401 | MS Railing Details | A3 | 1:5 | Pending | 1/4 day | 29/7/2021 | 29/7/2021 | LN
CUEA-SK-02-01-A-54401 | Step Details | A3 | 1:5 | Pending |  | 29/7/2021 | 29/7/2021 | LN
54500 | CEILING DETAILS
CUEA-SK-ZZ-01-A-54501 | Ceiling Details | A1 | 1:100 | Pending | 1/4 day | 30/7/2021 | 30/7/2021 | LN
57100 | SIGNS/PINBOARDS
CUEA-SK-ZZ-XX-A-57100 | Site Sign board | A1 | 1:100 | Done |  |  |  | GO
57200 | FITTINGS DETAILS
CUEA-SK-02-XX-A-57201 | Kitchenette Counter details | A4 | NTS | Pending | 1/2 day | 30/7/2021 | 30/7/2021 | LN
CUEA-SK-ZZ-06-A-57202 | Dhobi sink countertop details | A4 | NTS | Pending |  |  |  | LN
57300 | SANITARY FITTINGS DETAILS
CUEA-SK-ZZ-XX-A-57300 | Vanity Top Details | A1 | 1:100 | Pending | 1/4 day | 30/7/2021 | 30/7/2021 | LN
|  | KEY | PENDING
PARTIAL
DONE