## QWETU BLOCKS (A & B)
Project Name | PROPOSED CUEA HOSTELS FOR SPRUCE PROPERTIES LLP (PHASE 1)
Project Number | SK/20/2519
Project Stage | STAGE 5 -PRODUCTION INFORMATION
Date | 2021-12-03
Role | Company | Role
Client | SPRUCE PROPERTIES LLP | M & E | GDEA
Project Manager | ACORN | QS | BBK
Architect | SYMBION
Structural Engineer | GATH
Deliverables Schedule ( Qwetu Blocks)
Sheet Number | Drawing Title | Paper size | Scale | STATUS |  |  |  | Resource | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat
0000-999 | GENERAL |  |  |  | Duration | Start Date | End date |  | 2021-04-12 | 2021-04-13 | 2021-04-14 | 2021-04-15 | 2021-04-16 | 2021-04-17 | 2021-04-18 | 2021-04-19 | 2021-04-20 | 2021-04-21 | 2021-04-22 | 2021-04-23 | 2021-04-24 | 2021-04-25 | 2021-04-26 | 2021-04-27 | 2021-04-28 | 2021-04-29
CUEA-SK-ZZ-00-A-0010 | Hoarding details | A1 | 1:100 |  |  |  |  | CA
CUEA-SK-ZZ-00-A-0011 | Phase 1 and 2 Site Plan | A0 | 1:500 | Done |  |  |  | CA
CUEA-SK-ZZ-00-A-0012 | Proposed site plan -Zoned | A1 | 1:200 | Done |  |  |  | CA
CUEA-SK-ZZ-00-A-0013 | Site setting out plan | A1 | 1:200 | Done |  |  |  | CA
1000 -1999 | FLOOR PLANS
1100 | SETTING OUT
CUEA-SK-1.1-00-A-1101 | Ground Floor plan | A1 | 1:100 | Done |  |  |  | LN | bar: 2021-04-12
CUEA-SK-01-01-A-1102 | 1st floor plan | A1 | 1:100 | Done |  |  |  | LN | bar: 2021-04-12
CUEA-SK-01-XX-A-1103 | Typical 2nd and 3rd floors | A1 | 1:100 | Done |  |  |  | LN | bar: 2021-04-12
CUEA-SK-01-04-A-1104 | Fourth Floor | A1 | 1:100 | Done |  |  |  | LN | bar: 2021-04-12
CUEA-SK-01-06-A-1105 | Roof Level | A1 | 1:100 | Done |  |  |  | LN | bar: 2021-04-12
1300 | OPENINGS LAYOUTS
CUEA-SK-01-00-A-1301 | Ground Floor plan | A1 | 1:100 | Done |  |  |  | LN | bar: 2021-04-13
CUEA-SK-01-01-A-1302 | 1st floor plan | A1 | 1:100 | Done |  |  |  | LN | bar: 2021-04-13
CUEA-SK-01-XX-A-1303 | Typical 2nd and 3rd floors | A1 | 1:100 | Done |  |  |  | LN | bar: 2021-04-14
CUEA-SK-01-04-A-1304 | Fourth Floor | A1 | 1:100 | Done |  |  |  | LN | bar: 2021-04-14
CUEA-SK-01-05-A-1305 | Roof Terrace | A1 | 1:100 | Done |  |  |  | LN | bar: 2021-04-14
1400 | FINISHES LAYOUTS
CUEA-SK-1.1-00-A-1401 | Ground Floor plan | A1 | 1:100 | Done |  |  |  | LN | bar: 2021-04-15
CUEA-SK-01-01-A-1402 | 1st floor plan | A1 | 1:100 | Done |  |  |  | LN | bar: 2021-04-15
CUEA-SK-01-XX-A-1403 | Typical 2nd and 3rd floors | A1 | 1:100 | Done |  |  |  | LN | bar: 2021-04-15
CUEA-SK-01-04-A-1404 | Fourth Floor | A1 | 1:100 | Done |  |  |  | LN | bar: 2021-04-15
2000 | SECTIONS AND ELEVATIONS
CUEA-SK-1.1-XX-A-2001 | Section 2001 & 2002 | A1 | 1:100 | Done |  |  |  | LN | bar: 2021-04-16
CUEA-SK-01-XX-A-2011 | Elevation 2011 & 2012 | A1 | 1:100 | Done |  |  |  | LN | bar: 2021-04-16
CUEA-SK-01-XX-A-2012 | Elevation 2013 & 2014 | A1 | 1:100 | Done |  |  |  | LN | bar: 2021-04-16
3000 | BLOWUPS
CUEA-SK-01-04-A-3001 | Premium Studio layouts | A1 | 1:20 | Partial | 3 days |  |  | LN
CUEA-SK-01-XX-A-3002 | Twin room layouts | A1 | 1:20 | Partial |  |  |  | LN
CUEA-SK-01-XX-A-3003 | Standard studio room layouts | A1 | 1:20 | Partial |  |  |  | LN | bar: 2021-04-12
CUEA-SK-01-XX-A-3004 | Cluster room layouts | A1 | 1:20 | Partial |  |  |  | LN | bar: 2021-04-12
CUEA-SK-01-XX-A-3005 | Cluster room kitchen layouts | A1 | 1:20 | Partial |  | 2021-07-07 | 2021-09-07 | LN | bar: 2021-04-12
CUEA-SK-01-XX-A-34400 | Staircase 01 Blow up | A1 | 1:20 | Pending | 1 day | 2021-12-07 | 2021-12-07 | LN
CUEA-SK-01-XX-A-34401 | Staircase 02 Blow up | A1 | 1:20 | Pending |  |  |  | LN | bar: 2021-04-13
CUEA-SK-01-XX-A-34402 | Ramp Blow up | A1 | 1:20 | Pending |  |  |  | LN
CUEA-SK-01-XX-A-34403 | Steps Blow up | A1 | 1:20 | Pending |  |  |  | LN | bar: 2021-04-14
CUEA-SK-01-XX-A-37100 | Laundry Area | A3 | 1:20 | Pending |  |  |  | LN
42100 | EXTERNAL WALL SCHEDULES
CUEA-SK-ZZ-XX-A-42100 | 200mm Thick Masonry Wall | A4 | 1:5 | Pending | 1 days | 13/7/2021 | 13/7/2021 | LN
CUEA-SK-ZZ-XX-A-42101 | 250mm Thick RC Wall | A4 | 1:5 | Pending |  | 13/7/2021 | 13/7/2021 | LN
CUEA-SK-ZZ-XX-A-42102 | 150mm Thick Masonry Wall | A4 | 1:5 | Pending |  | 13/7/2021 | 13/7/2021 | LN
CUEA-SK-ZZ-XX-A-42103 | 100mm Thick Masonry Wall | A4 | 1:5 | Pending |  | 13/7/2021 | 13/7/2021 | LN
CUEA-SK-01-XX-A-42104 | 20mm MDF partition wall | A4 | 1:5 | Pending |  | 13/7/2021 | 13/7/2021 | LN | bar: 2021-04-19
43000 | DOOR & WINDOW SCHEDULES
CUEA-SK-01-XX-A-43000 | Door Schedules | A3 | 1:20 | Partial | 1 day | 15/7/2021 | 15/7/2021 | LN | bar: 2021-04-20
CUEA-SK-01-XX-A-43010 | Window Schedules | A3 | 1:20 | Done |  | 15/7/2021 | 15/7/2021 | LN | bar: 2021-04-21 to 2021-04-22
CUEA-SK-01-XX-A-43011 | Curtain Wall Details | A1 | 1:20 | Done |  | 15/7/2021 | 15/7/2021 | LN | bar: 2021-04-22
CUEA-SK-01-XX-S-43050 | Iron Mongery schedule | A4 | NTS | Done |  |  |  | CA
44000 | FINISHES SCHEDULES
CUEA-SK-ZZ-XX-S-44000 | Finishes and Specifications schedules | A4 | NTS | Partial | 1 day | 13/7/2021 | 13/7/2021 | CA
45000 | SANITARY SCHEDULES
CUEA-SK-ZZ-XX-S-45000 | Sanitary and accessories schedules | A1 | 1:100 | Partial | 1 day | 14/7/2021 | 14/7/2021 | CA
52100 | EXTERNAL WALL DETAILS
CUEA-SK-01-01-A-52100 | External wall details | A3 | 1:10 | Pending | 1/2 day | 15/7/2021 | 15/7/2021 | LN
CUEA-SK-01-01-A-52101 | Internal wall details | A3 | 1:10 | Pending |  | 15/7/2021 | 15/7/2021 | LN
52200 | EXTERNAL WALL DETAILS
CUEA-SK-01-01-A-52200 | Twin Room Partition Wall | A3 | 1:10 | Pending | 1/4 day | 15/7/2021 | 15/7/2021 | LN | bar: 2021-04-23
52700 | EXTERNAL WALL DETAILS
CUEA-SK-01-01-A-52700 | Roof Details | A3 | 1:10 | Pending | 2 day |  |  | CA
CUEA-SK-01-01-A-52701 | Canopy Details | A3 | 1:10 | Pending |  | 15/7/2021 | 16/7/2021 | CA | bar: 2021-04-26 to 2021-04-27
53200 | ASSEMBLY DETAILS
CUEA-SK-ZZ-XX-A-53200 | Window Sill, Jamb & head details | A3 | 1:5 | Pending | 1/4 day | 15/7/2021 | 15/7/2021 | LN
CUEA-SK-ZZ-XX-A-53201 | Door Jamb & head details | A3 | 1:5 | Pending |  | 15/7/2021 | 15/7/2021 | LN
53400 | HANDRAIL AND BARRIER DETAILS
CUEA-SK-ZZ-XX-A-53400 | MS Balustrade details | A3 | 1:5 | Pending | 1/4 day | 16/7/2021 | 16/7/2021 | LN
CUEA-SK-ZZ-05-A-53401 | Safety mesh details | A3 | 1:10 | Pending |  | 16/7/2021 | 16/7/2021 | LN
CUEA-SK-ZZ-01-A-53402 | Palisade Fence Details | A3 | 1:10 | Pending |  | 16/7/2021 | 16/7/2021 | LN
54100 | EXTERNAL WALL FINISHES DETAILS
CUEA-SK-ZZ-XX-A-54100 | Coping Details | A3 | 1:5 | Pending | 1/8 day | 16/7/2021 | 16/7/2021 | LN | bar: 2021-04-27
54200 | INTERNAL WALL FINISHES DETAILS
CUEA-SK-ZZ-XX-A-54200 | Skirting details MDF and Tile | A3 | 1:5 | Pending | 1/8 day | 16/7/2021 | 16/7/2021 | LN
54300 | INTERNAL FLOOR FINISHES DETAILS
CUEA-SK-ZZ-00-A-54301 | Mattwell detail | A3 | 1:5 | Pending | 1/4 day | 16/7/2021 | 16/7/2021 | LN
CUEA-SK-ZZ-00-A-54302 | Door threshold details | A3 | 1:5 | Pending |  | 16/7/2021 | 16/7/2021 | LN
54400 | STAIRCASE AND RAMP DETAILS
CUEA-SK-ZZ-XX-A-54401 | MS Railing Details | A3 | 1:5 | Pending | 1/4 day | 16/7/2021 | 16/7/2021 | LN
CUEA-SK-ZZ-XX-A-54401 | Step Details | A3 | 1:5 | Pending |  | 16/7/2021 | 16/7/2021 | LN | bar: 2021-04-28
54500 | CEILING DETAILS
CUEA-SK-ZZ-01-A-54501 | Ceiling Details | A1 | 1:100 | Pending | 1/4 day | 19/7/2021 | 19/7/2021 | LN
57100 | SIGNS/PINBOARDS
CUEA-SK-ZZ-00-A-57100 | Site Sign board | A1 | 1:100 | Done |  |  |  | GO
57200 | FITTINGS DETAILS
CUEA-SK-01-XX-A-57201 | Kitchenette Counter details | A4 | NTS | Pending | 1/2 day | 19/7/2021 | 19/7/2021 | LN
CUEA-SK-01-05-A-57203 | Dhobi sink countertop details | A4 |  | Pending |  | 19/7/2021 | 19/7/2021 | LN
57300 | SANITARY FITTINGS DETAILS
CUEA-SK-ZZ-XX-A-57300 | Vanity Top Details | A1 | 1:100 | Pending | 1/4 day | 19/7/2021 | 19/7/2021 | LN | bar: 2021-04-29
|  | KEY | PENDING
PARTIAL
DONE

## QEJANI BLOCK (Double & Quad)
Project Name | PROPOSED CUEA HOSTELS FOR SPRUCE PROPERTIES LLP (PHASE 1)
Project Number | SK/20/2519
Project Stage | STAGE 5 -PRODUCTION INFORMATION
Date | 2021-12-03
Role | Company | Role
Client | SPRUCE PROPERTIES LLP | M & E | GDEA
Project Manager | ACORN | QS | BBK
Architect | SYMBION
Structural Engineer | GATH
Deliverables Schedule (Qejani Double and Quad)
Sheet Number | Drawing Title | Paper size | Scale | STATUS |  |  |  | Resource
0000-999 | GENERAL |  |  |  | Duration | Start Date | End date
CUEA-SK-ZZ-00-A-0011 | Phase 1 and 2 Site Plan | A0 | 1:500 | Done |  |  |  | CA
CUEA-SK-ZZ-00-A-0012 | Proposed site plan -Zoned | A1 | 1:200 | Done |  |  |  | CA
CUEA-SK-ZZ-00-A-0013 | Site setting out plan | A1 | 1:200 | Done |  |  |  | CA
1100 | SETTING OUT
CUEA-SK-2.4-00-A-1101 | Ground & First Floor plan | A1 | 1:100 | Done |  |  |  | LN
CUEA-SK-2.1-XX-A-1102 | Typical & Fourth Floor Plan | A1 | 1:100 | Done |  |  |  | LN
CUEA-SK-2.1-05-A-1103 | Roof Terrace & Upper Roof Plan | A1 | 1:100 | Done |  |  |  | LN
1300 | OPENINGS LAYOUTS
CUEA-SK-2.4-00-A-1301 | Ground & First Floor | A1 | 1:100 | Done |  |  |  | LN
CUEA-SK-2.1-XX-A-1302 | Typical & Fourth Floor Plan | A1 | 1:100 | Done |  |  |  | LN
CUEA-SK-2.1-0 5-A-1303 | Roof Terrace | A1 | 1:100 | Done |  |  |  | LN
1400 | FINISHES LAYOUTS
CUEA-SK-2.4-00-A-1401 | Ground & First Floor | A1 | 1:100 | Partial |  | 21/07/2021 | 21/07/2021 | LN
CUEA-SK-2.1-XX-A-1402 | Typical & Fourth Floor | A1 | 1:100 | Partial |  | 21/07/2021 | 21/07/2021 | LN
CUEA-SK-2.1-05-A-1403 | Roof Terrace | A1 | 1:100 | Partial |  | 21/07/2021 | 21/07/2021 | LN
2000 | SECTIONS AND ELEVATIONS
CUEA-SK-02-XX-A-2001 | Section 2001 & 2002 | A1 | 1:100 | Done | 1 day |  |  | LN
CUEA-SK-02-XX-A-2002 | Elevation 2003 & 2004 | A1 | 1:100 | Done |  |  |  | LN
CUEA-SK-02-XX-A-2003 | Elevation 2005 & 2006 | A1 | 1:100 | Done |  |  |  | LN
3000 | BLOWUPS
CUEA-SK-2.1-XX-A-3001 | Double Room | A1 | 1:20 | Pending | 1 day | 23/7/2021 | 23/7/2031 | LN
CUEA-SK-2.1-XX-A-3002 | Kitchenette Room | A1 | 1:20 | Pending |  |  |  | LN
|  |  |  | Pending |  |  |  | LN
CUEA-SK-02-XX-A-34400 | Staircase 01 Blow up | A1 | 1:20 | Done |  |  |  | LN
CUEA-SK-02-XX-A-34401 | Staircase 02 Blow up | A1 | 1:20 | Done |  |  |  | LN
CUEA-SK-02-XX-A-34402 | Ramp Blow up | A1 | 1:20 | Pending |  |  |  | LN
CUEA-SK-02-XX-A-34403 | Steps Blow up | A1 | 1:20 | Pending |  |  |  | LN
|  |  |  | Pending |  |  |  | LN
CUEA-SK-2.1-XX-A-37100 | Residents Washrooms | A3 | 1:20 | Pending |  |  |  | LN
CUEA-SK-2.1-XX-A-37101 | Laundry Area | A3 | 1:20 | Pending |  |  |  | LN
42100 | EXTERNAL WALL SCHEDULES
CUEA-SK-ZZ-XX-A-42100 | 200mm Thick Masonry Wall | A4 | 1:5 | Pending | 1/2 day | 26/7/2021 | 26/4/2021 | LN
CUEA-SK-ZZ-XX-A-42101 | 250mm Thick RC Wall | A4 | 1:5 | Pending |  |  |  | LN
CUEA-SK-ZZ-XX-A-42102 | 150mm Thick Masonry Wall | A4 | 1:5 | Pending |  |  |  | LN
CUEA-SK-ZZ-XX-A-42103 | 100mm Thick Masonry Wall | A4 | 1:5 | Pending |  |  |  | LN
43000 | DOOR & WINDOW SCHEDULES
CUEA-SK-2.1-XX-S-43000 | Door Schedules | A3 | 1:20 | Partial | 1/2 day | 26/7/2021 | 26/7/2021 | LN
CUEA-SK-2.1-XX-S-43010 | Window Schedules | A3 | 1:20 | Done |  |  |  | LN
CUEA-SK-XX-XX-S-43050 | Iron Mongery schedule | A4 | NTS | Done |  |  |  | CA
44000 | FINISHES SCHEDULES
CUEA-SK-ZZ-XX-S-44000 | Finishes and Specifications schedules | A4 | NTS | Pending | 1 day | 27/7/2021 | 27/7/2021 | CA
45000 | SANITARY SCHEDULES
CUEA-SK-ZZ-XX-S-45000 | Sanitary and accessories schedules | A1 | 1:100 | Partial | 1 day | 27/7/2021 | 27/7/2021 | CA
52100 | EXTERNAL WALL DETAILS
CUEA-SK-2.1-XX-A-52100 | External wall details | A3 | 1:10 | Pending | 1/2 day | 27/7/2021 | 27/7/2021 | LN
CUEA-SK-2.1-XX-A-52101 | Internal wall details | A3 | 1:10 | Pending |  |  |  | LN
52700 | ROOF DETAILS
CUEA-SK-02-06-A-52700 | Roof Details | A3 | 1:10 | Pending | 1/2 day |  |  | LN
CUEA-SK-02-01-A-52701 | Canopy Details | A3 | 1:10 | Pending |  | 27/7/2021 | 27/7/2021 | LN
53200 | ASSEMBLY DETAILS
CUEA-SK-ZZ-XX-A-53200 | Window Sill, Jamb & head details | A3 | 1:5 | Pending | 1/2 day | 28/7/2021 | 28/7/2021 | LN
CUEA-SK-ZZ-XX-A-53201 | Door Jamb & head details | A3 | 1:5 | Pending |  | 28/7/2021 | 28/7/2021 | LN
53400 | HANDRAIL AND BARRIER DETAILS
CUEA-SK-ZZ-XX-A-53400 | MS Balustrade details | A3 | 1:5 | Pending | 1/2 day | 28/7/2021 | 28/7/2021 | LN
CUEA-SK-ZZ-05-A-53401 | Safety mesh details | A3 | 1:10 | Pending |  | 28/7/2021 | 28/7/2021 | LN
CUEA-SK-ZZ-00-A-53402 | Palisade Fence Details | A3 | 1:10 | Pending |  | 28/7/2021 | 28/7/2021 | LN
54100 | EXTERNAL WALL FINISHES DETAILS
CUEA-SK-ZZ-XX-A-54100 | Coping Details | A3 | 1:5 | Pending | 1/4 day | 29/7/2021 | 29/7/2021 | LN
54200 | INTERNAL WALL FINISHES DETAILS
CUEA-SK-ZZ-XX-A-54200 | Skirting details MDF and Tile | A3 | 1:5 | Pending | 1/4 day | 29/7/2021 | 29/7/2021 | LN
54300 | INTERNAL FLOOR FINISHES DETAILS
CUEA-SK-ZZ-00-A-54301 | Mattwell detail | A3 | 1:5 | Pending | 1/4 day | 29/7/2021 | 29/7/2021 | LN
CUEA-SK-ZZ-XX-A-54302 | Door threshold details | A3 | 1:5 | Pending |  | 29/7/2021 | 29/7/2021 | LN
54400 | STAIRCASE AND RAMP DETAILS
CUEA-SK-02-01-A-54401 | MS Railing Details | A3 | 1:5 | Pending | 1/4 day | 29/7/2021 | 29/7/2021 | LN
CUEA-SK-02-01-A-54401 | Step Details | A3 | 1:5 | Pending |  | 29/7/2021 | 29/7/2021 | LN
54500 | CEILING DETAILS
CUEA-SK-ZZ-01-A-54501 | Ceiling Details | A1 | 1:100 | Pending | 1/4 day | 30/7/2021 | 30/7/2021 | LN
57100 | SIGNS/PINBOARDS
CUEA-SK-ZZ-XX-A-57100 | Site Sign board | A1 | 1:100 | Done |  |  |  | GO
57200 | FITTINGS DETAILS
CUEA-SK-02-XX-A-57201 | Kitchenette Counter details | A4 | NTS | Pending | 1/2 day | 30/7/2021 | 30/7/2021 | LN
CUEA-SK-ZZ-06-A-57202 | Dhobi sink countertop details | A4 | NTS | Pending |  |  |  | LN
57300 | SANITARY FITTINGS DETAILS
CUEA-SK-ZZ-XX-A-57300 | Vanity Top Details | A1 | 1:100 | Pending | 1/4 day | 30/7/2021 | 30/7/2021 | LN
|  | KEY | PENDING
PARTIAL
DONE

## Timelines
Project Name | PROPOSED PBSA AT HURLINGHAM FOR BEECH PROPERTIES LLP (PHASE 1)
Project Number | SK/17/2428
Project Stage | STAGE 4.1
Date | 2019-10-16
DELIVERABLES |  | START DATE | END DATE | RESOURSE
REVIT MODEL
SPECIFICATIONS
SCHEDULES | ROOM SCHEDULE
Premiun Studio
Standart Studio
Twin Room
Cluster Room
Cluster Kitchen
WINDOW LAYOUTS & SCHEDULE
Window & Curtain wall schedule
Ground floor window openings layout
1st floor window openings layout
Typical floor window openings layout
Roof terrace floor window openings layout
DOOR LAYOUTS & SCHEDULE
Door schedule
Ground floor door openings layout
1st floor door openings layout
Typical floor door openings layout
Roof terrace floor door openings layout
Basement door openings layout
Security building door openings layout
DETAILS | VERTICAL CIRCULATION DETAILS
North & south Wing Staircase sections
North wing stair layouts
South wing stair layouts
North & South wing staircase details
EXTERNAL WALL DETAILS
Curtain wall details
External wall details
INTERNAL WALL DETAILS
Gypsum board partition details
Aluminium frame partition details
ROOF DETAILS
Roof, parapet wall & canopy details
ASSEMBLY DETAILS
Window Sill, Jamb & head details
Door Jamb & head details
BALUSTRADE DETAILS
MS Balustrade details
Glass Balustrade details
INTERNAL WALL FINISHES DETAILS
Skirting details
INTERNAL FLOOR DETAILS
Mattwell detail
Door threshold details
FIRE SAFETY DETAILS
Vertical fire stop details
Horizontal fire stop details
Fire Hose-reel cupboard details
SIGNS/PINBOARDS
Site signboard details
Signage schedule & detail
BUILT IN FURNITURE(72s)
Security building in-built furniture details
Room in-built furniture details
BUILT IN FURNITURE(73s)
Cluster Kitchen details
BUILT IN SANITARY FITTINGS DETAILS
GF Public Washrooms details
Roof terrace WC details
Laundry details
Security building WC details
EXTERNAL WORKS DETAILS
Boundary wall type A & B detail
Gate details
Paver details
Planter details
Entry court planter details
Bollard details
Hoarding details
LAYOUTS | SETTING OUT DRAWINGS
Existing site plan
Proposed site plan
Site setting out plan
Ground floor setting out part plan - 1
Ground floor setting out part plan - 2
1st floor setting out part plan - 1
1st floor setting out part plan - 2
2nd floor setting out part plan - 1
2nd floor setting out part plan - 2
4th floor setting out part plan - 1
4th floor setting out part plan - 2
5th floor setting out part plan - 1
5th floor setting out part plan - 2
Typical floor (3, 6-14th) setting out part plan - 1
Typical floor (3, 6-14th) setting out part plan - 2
Roof terrace setting out part plan - 1
Roof terrace setting out part plan - 2
SECTIONS
Section A-A
Section B-B & Section C-C
Section D-D
Section E-E & Section F-F
Basement Section
ELEVATIONS
East Elevation
North Elevation
South Elevation
West elevation
Courtyard elevations
INTERIOR DESIGN | LAYOUTS
Reception & Waiting
Lounges
Lift Lobbies
Study Rooms
Ceiling details
REVIEW

## Zones
Project Name | PROPOSED PBSA AT HURLINGHAM FOR BEECH PROPERTIES LLP (PHASE 1)
Project Number | SK/17/2428
Project Stage | STAGE 4.1
Date | 2018-11-27
LOCATION | ZONES
GROUND FLOOR | 01. Reception & Management
Academic zone - North Wing
Amenities zone - Central Wing
Staff zone - South Wing
1ST - 14TH FLOOR | Twin Rooms
Standard Studios
Premium Roosm
Cluster zone
15 FLOOR | Lounge
Washing & Washrooms
Terraces
ROOF | Roof
BASEMENT | Basement
CIRCULATION | Staircases
Lifts zone
Ramps
Corridors
EXTERNAL WORKS | Gate House
Boundary Walls
External Walls
Civil Works

## Finishes schedule (hidden)
Project Name | PROPOSED PBSA AT HURLINGHAM FOR BEECH PROPERTIES LLP
Project Number | SK/17/2428
Project Stage | STAGE 4.2 - TECHNICAL DESIGN _PD
Date | 2018-11-02
INTERIOR FINISHES SCHEDULE
Room number | Room name | Floor finish | Skirting | Wall finish | Ceiling
GROUNDFLOOR
| Reception | M40.1 Anti-slip tile 2 600x600x10mm Slip rating R11 | M40.1.1 Ceramic tile 600x100x8.4mm | M20.1 & M60.1 15mm plaster with 3 coats of silk paint ; 3 coats of white silk paint | M20.2 & M60.2 Gyproc skimming and Hi-matt emulsion paint
| My waiting space | M40.1 Anti-slip tile 2 600x600x10mm Slip rating R11 | M40.1.1 Ceramic tile 600x100x8.4mm | M20.1 & M60.1 15mm plaster with 3 coats of silk paint ; 3 coats of white silk paint | M20.2 & M60.2 Gyproc skimming and Hi-matt emulsion paint
| Corridor | M40.1 Anti-slip tile 2 600x600x10mm Slip rating R11 | M40.1.1 Ceramic tile 600x100x8.4mm | Exposed fair-faced concrete for block work; M20.1 & M60.1 15mm plaster with 3 coats of silk paint ; 3 coats of white silk paint | M20.2 & M60.2 Gyproc skimming and Hi-matt emulsion paint
| Lift lobby | M40.1 Anti-slip tile 3 600x600x10mm Slip rating R11 | M40.1.1 Ceramic tile 600x100x8.4mm | M20.1 & M60.1 15mm plaster with 3 coats of silk paint ; 3 coats of white silk paint | M20.2 & M60.2 Gyproc skimming and Hi-matt emulsion paint
| Staircore 1& 2 | M40.1 Anti-slip tile 3 600x600x10mm Slip rating R11 | M40.1.1 Ceramic tile 600x100x8.4mm | M60.1 3 coats of white silk paint | M20.2 & M60.2 Gyproc skimming and Hi-matt emulsion paint
| Public toilets | M40.1 Anti-slip tile 3 600x600x10mm Slip rating R11 |  | M40.1.2 300x100x8.4mm (15mm plaster, 4mm grouting) | M20.2 & M60.2 Gyproc skimming and Hi-matt emulsion paint
| Management office | M50.1 Carpet tile | P20.1 100mm high MDF | M20.1 & M60.1 15mm plaster with 3 coats of silk paint | M20.2 & M60.2 Gyproc skimming and Hi-matt emulsion paint
| Office | M50.1 Carpet tile | P20.1 100mm high MDF | M20.1 & M60.1 15mm plaster with 3 coats of silk paint | M20.2 & M60.2 Gyproc skimming and Hi-matt emulsion paint
| Library | M50.1 & M50.2 Carpet tile & vinyl flooring | P20.1 100mm high MDF | M20.1 & M60.1 15mm plaster with 3 coats of silk paint | M20.2 & M60.2 Gyproc skimming and Hi-matt emulsion paint
| Chat space | M50.1 & M50.2 Carpet tile & vinyl flooring | P20.1 100mm high MDF | M20.1 & M60.1 15mm plaster with 3 coats of silk paint | M20.2 & M60.2 Gyproc skimming and Hi-matt emulsion paint
| Chill-out lounge | M50.1 & M50.2 Carpet tile & vinyl flooring | P20.1 100mm high MDF | M20.1 & M60.1 15mm plaster with 3 coats of silk paint | M20.2 & M60.2 Gyproc skimming and Hi-matt emulsion paint
| Reading rooms | M50.1 Carpet tile | P20.1 100mm high MDF | M20.1 & M60.1 15mm plaster with 3 coats of silk paint | M20.2 & M60.2 Gyproc skimming and Hi-matt emulsion paint
| Gaming space | M50.2 Vinyl flooring(wood pattern) | P20.1 100mm high MDF | M20.1 & M60.1 15mm plaster with 3 coats of silk paint | M20.2 & M60.2 Gyproc skimming and Hi-matt emulsion paint
| My eating space | M50.2 Vinyl flooring(wood pattern) | P20.1 100mm high MDF | M20.1 & M60.1 15mm plaster with 3 coats of silk paint | M20.2 & M60.2 Gyproc skimming and Hi-matt emulsion paint
| Shop | M40.1 Anti-slip tile 1 600x600x10mm Slip rating R11 | M40.1.1 Ceramic tile 600x100x8.4mm | M20.1 & M60.1 15mm plaster with 3 coats of silk paint | M20.2 & M60.2 Gyproc skimming and Hi-matt emulsion paint
| Kitchen serving | M40.1 Anti-slip tile 1 600x600x10mm Slip rating R11 | M40.1.1 Ceramic tile 600x100x8.4mm | M20.1 & M60.1 15mm plaster with 3 coats of silk paint | M20.2 & M60.2 Gyproc skimming and Hi-matt emulsion paint
| Kitchen prep | M40.1 Anti-slip tile 1 600x600x10mm Slip rating R11 |  | M20.1 & M60.1 15mm plaster with 3 coats of silk paint | M20.2 & M60.2 Gyproc skimming and Hi-matt emulsion paint
| Plant room | M10.1 Monolithic screed | M10.1.1 monolithic screed | M60.1 3 coats of white silk paint | M20.2 & M60.2 Gyproc skimming and Hi-matt emulsion paint
| Dev MX | M10.1 Monolithic screed | M10.1.1 monolithic screed | M60.1 3 coats of white silk paint | M20.2 & M60.2 Gyproc skimming and Hi-matt emulsion paint
| TRX | M10.1 Monolithic screed | M10.1.1 monolithic screed | M60.1 3 coats of white silk paint | M20.2 & M60.2 Gyproc skimming and Hi-matt emulsion paint
| Storage, housekeeping & merchandise | M10.1 Monolithic screed | M10.1.1 monolithic screed | M60.1 3 coats of white silk paint | M20.2 & M60.2 Gyproc skimming and Hi-matt emulsion paint
| Refuse room | M10.1 Monolithic screed | M10.1.1 monolithic screed | M60.1 3 coats of white silk paint | M20.2 & M60.2 Gyproc skimming and Hi-matt emulsion paint
| Covered Terrace | M42.1 Composite deck
| Exterior walkways | Q25.1 PCC paving slabs
1st Floor & typical floors
| Lift lobby | M40.1 Anti-slip tile 3 600x600x10mm Slip rating R11 | M40.1.1 Ceramic tile 600x100x8.4mm | M20.1 & M60.1 15mm plaster with 3 coats of silk paint ; 3 coats of white silk paint | M20.2 & M60.2 Gyproc skimming and Hi-matt emulsion paint
| Staircore 1& 2 | M40.1 Anti-slip tile 3 600x600x10mm Slip rating R11 | M40.1.1 Ceramic tile 600x100x8.4mm | M60.1 3 coats of white silk paint | M20.2 & M60.2 Gyproc skimming and Hi-matt emulsion paint
| Twin rooms | M40.1 Anti-slip tile 1 600x600x10mm Slip rating R11 | P20.1 100mm high MDF | M20.1 & M60.1 Room: 15mm plaster with 3 coats of silk paint | M20.2 & M60.2 Gyproc skimming and Hi-matt emulsion paint
|  |  |  | M40.1.2 Kitchenette & bath : 300x100x8.4mm (15mm plaster, 4mm grouting) | M20.2 & M60.2 Gyproc skimming and Hi-matt emulsion paint
| Cluster rooms | M40.1 Anti-slip tile 1 600x600x10mm Slip rating R11 | P20.1 100mm high MDF | M20.1 & M60.1 Room: 15mm plaster with 3 coats of silk paint | M20.2 & M60.2 Gyproc skimming and Hi-matt emulsion paint
|  |  |  | M40.1.2 Kitchenette & bath : 300x100x8.4mm (15mm plaster, 4mm grouting) | M20.2 & M60.2 Gyproc skimming and Hi-matt emulsion paint
| Premium studio | M40.1 Anti-slip tile 1 600x600x10mm Slip rating R11 | P20.1 100mm high MDF | M20.1 & M60.1 Room: 15mm plaster with 3 coats of silk paint | M20.2 & M60.2 Gyproc skimming and Hi-matt emulsion paint
|  |  |  | M40.1.2 Kitchenette & bath : 300x100x8.4mm (15mm plaster, 4mm grouting) | M20.2 & M60.2 Gyproc skimming and Hi-matt emulsion paint
| Standard studio | M40.1 Anti-slip tile 1 600x600x10mm Slip rating R11 | P20.1 100mm high MDF | M20.1 & M60.1 Room: 15mm plaster with 3 coats of silk paint | M20.2 & M60.2 Gyproc skimming and Hi-matt emulsion paint
|  |  |  | M40.1.2 Kitchenette & bath : 300x100x8.4mm (15mm plaster, 4mm grouting) | M20.2 & M60.2 Gyproc skimming and Hi-matt emulsion paint
| Cluster Kitchen | M40.1 Anti-slip tile 1 600x600x10mm Slip rating R11 |  | M20.1 & M60.1 Room: 15mm plaster with 3 coats of silk paint | M20.2 & M60.2 Gyproc skimming and Hi-matt emulsion paint
|  |  |  | M40.1.2 Kitchenette & bath : 300x100x8.4mm (15mm plaster, 4mm grouting) | M20.2 & M60.2 Gyproc skimming and Hi-matt emulsion paint
| Corridor | M40.1 Anti-slip tile 2 600x600x10mm Slip rating R11 | M40.1.1 Ceramic tile 600x100x8.4mm | Exposed fair-faced concrete for block work; M20.1 & M60.1 15mm plaster with 3 coats of silk paint ; 3 coats of white silk paint | M20.2 & M60.2 Gyproc skimming and Hi-matt emulsion paint
Roof terrace
| Lift lobby | M40.1 Anti-slip tile 3 600x600x10mm Slip rating R11 | M40.1.1 Ceramic tile 600x100x8.4mm | M20.1 & M60.1 15mm plaster with 3 coats of silk paint ; 3 coats of white silk paint | M20.2 & M60.2 Gyproc skimming and Hi-matt emulsion paint
| Staircore 1& 2 | M40.1 Anti-slip tile 3 600x600x10mm Slip rating R11 | M40.1.1 Ceramic tile 600x100x8.4mm | M60.1 3 coats of white silk paint | M20.2 & M60.2 Gyproc skimming and Hi-matt emulsion paint
| Corridor | M40.1 Anti-slip tile 2 600x600x10mm Slip rating R11 | M40.1.1 Ceramic tile 600x100x8.4mm | Exposed fair-faced concrete for block work; M20.1 & M60.1 15mm plaster with 3 coats of silk paint ; 3 coats of white silk paint | M20.2 & M60.2 Gyproc skimming and Hi-matt emulsion paint
| Toilets | M40.1 Anti-slip tile 3 600x600x10mm Slip rating R11 |  | M40.1.2 300x100x8.4mm (15mm plaster, 4mm grouting) | M20.2 & M60.2 Gyproc skimming and Hi-matt emulsion paint
| Laundry | M40.1 Anti-slip tile 1 600x600x10mm Slip rating R11 |  | M20.1 & M60.1 15mm plaster with 3 coats of silk paint 3 coats of white silk paint M40.1.2 2 rows of 300x100x8.4mm ceramic tile splashback above worktop | M20.2 & M60.2 Gyproc skimming and Hi-matt emulsion paint
| Entertainment lounge | M40.1 Anti-slip tile 1 600x600x10mm Slip rating R11 |  | M20.1 & M60.1 15mm plaster with 3 coats of silk paint | M20.2 & M60.2 Gyproc skimming and Hi-matt emulsion paint
| Drying yard | M40.2 Interlocking concrete tiles
| Open terraces | M50.4 Astro turf
| Open terraces | M42.1 Composite deck
| Gaming room | M50.1 Carpet tile | P20.1 100mm high MDF | M20.1 & M60.1 15mm plaster with 3 coats of silk paint | M20.2 & M60.2 Gyproc skimming and Hi-matt emulsion paint
| Open lounge | M50.1 & M50.2 Carpet tile & vinyl flooring | P20.1 100mm high MDF | M20.1 & M60.1 15mm plaster with 3 coats of silk paint | M20.2 & M60.2 Gyproc skimming and Hi-matt emulsion paint
| Chill-out lounge | M50.1 & M50.2 Carpet tile & vinyl flooring | P20.1 100mm high MDF | M20.1 & M60.1 15mm plaster with 3 coats of silk paint | M20.2 & M60.2 Gyproc skimming and Hi-matt emulsion paint
| Movie room | M50.1 Carpet tile | P20.1 100mm high MDF | M20.1 & M60.1 15mm plaster with 3 coats of silk paint | M20.2 & M60.2 Gyproc skimming and Hi-matt emulsion paint
| Gym(Ladies, Men, Yoga) | M50.3 Rubber floor tile | P20.1 100mm high MDF | M20.1 & M60.1 15mm plaster with 3 coats of silk paint | M20.2 & M60.2 Gyproc skimming and Hi-matt emulsion paint