## TG KAWA
Project Name | KAWA HOUSING DEVELOPMENT FOR TRUE GROUP
Project Number | SK/22/2577
Project Stage | STAGE 4.1 -DETAIL DESIGN
Date | 2022-06-02
Role | Company | Role
Client | TG KAWA LIMITED | M & E
Project Manager |  | QS
Architect | SYMBION
Structural Engineer
Deliverables Schedule
Sheet Number | Drawing Title | Paper size | Scale | STATUS
0000 | GENERAL
2577-SK-00-DR-A-0001 | Site Plan | A1 | 1:100 | Partial
1100 | SETTING OUT
2577-SK-00-DR-A-1101 | Ground Floor | A1 | 1:100 | Pending
2577-SK-01-DR-A-1102 | First Floor | A1 | 1:100 | Pending
2577-SK-02-DR-A-1103 | Typical 2nd-7th Floor | A1 | 1:100 | Pending
2577-SK-07-DR-A-1104 | Roof Terrace Level | A1 | 1:100 | Pending
2577-SK-15-DR-A-1105 | Upper Roof Level | A1 | 1:100 | Pending
1200 | GENERAL ARRANGEMENT
2577-SK-00-DR-A-1201 | Ground Floor | A1 | 1:100 | Partial
2577-SK-03-DR-A-1202 | First Floor | A1 | 1:100 | Partial
2577-SK-07-DR-A-1203 | Typical 2nd-7th Floor | A1 | 1:100 | Partial
2577-SK-15-DR-A-1204 | Roof Terrace Level | A1 | 1:100 | Partial
2577-SK-16-DR-A-1205 | Upper Roof Level | A1 | 1:100 | Partial
1300 | OPENINGS LAYOUTS
2577-SK-00-DR-A-1301 | Ground Floor | A1 | 1:100 | Pending
2577-SK-01-DR-A-1302 | First Floor | A1 | 1:100 | Pending
2577-SK-01-DR-A-1303 | Typical 2nd-7th Floor | A1 | 1:100 | Pending
2577-SK-01-DR-A-1304 | Roof Terrace Level | A1 | 1:100 | Pending
1400 | FINISHES LAYOUTS
2577-SK-00-DR-A-1401 | Ground Floor | A1 | 1:100 | Pending
2577-SK-01-DR-A-1402 | First Floor | A1 | 1:100 | Pending
2577-SK-02-DR-A-1403 | Typical 2nd-7th Floor | A1 | 1:100 | Pending
2577-SK-07-DR-A-1404 | Roof Terrace Level | A1 | 1:100 | Pending
2577-SK-15-DR-A-1405 | Upper Roof Level | A1 | 1:100 | Pending
2000 | SECTIONS AND ELEVATIONS
2577-SK-XX-DR-A-2001 | Elevation 01 | A1 | 1:100 | Partial
2577-SK-XX-DR-A-2002 | Elevation 02 | A1 | 1:100 | Partial
2577-SK-XX-DR-A-2003 | Elevation 03 | A1 | 1:100 | Partial
2577-SK-XX-DR-A-2004 | Elevation 04 | A1 | 1:100 | Partial
2577-SK-XX-DR-A-2100 | Section 01 | A1 | 1:100 | Partial
3000 | BLOWUPS
2577-SK-XX-DR-A-3001 | Standard Studio Blowup | A1 | 1:100 | Partial
2577-SK-XX-DR-A-3002 | Double Room Blow Up | A1 | 1:100
34400 | STAIRCASE AND RAMP BLOWUPS
2577-SK-XX-DR-A-34401 | Ground Floor Staircase | A1 | 1:100 | Pending
2577-SK-XX-DR-A-34400 | Typical Floor Staircase | A1 | 1:100 | Pending
42100 | EXTERNAL WALL SCHEDULES
2577-SK-ZZ-DR-A-42100 | 200mm Thick Masonry Wall | A4 | 1:5 | Pending
2577-SK-ZZ-DR-A-42101 | 150mm Thick Masonry Wall | A4 | 1:5 | Pending
2577-SK-ZZ-DR-A-42102 | 100mm Thick Masonry Wall | A4 | 1:5 | Pending
43000 | DOOR & WINDOW SCHEDULES
2577-SK-ZZ-SH-A-43101 | Door Schedule | A4 | 1:20 | Pending
2577-SK-ZZ-SH-A-43102 | Window Schedule | A4 | 1:20 | Pending
2577-SK-XX-SH-A-43050 | Iron Mongery schedule | A4 | NTS | Pending
44000 | FINISHES SCHEDULES
2577-SK-ZZ-SH-A-44000 | Finishes and Specifications schedules | A4 | NTS | Pending
52100 | EXTERNAL WALL DETAILS
2577-SK-XX-DR-A-52100 | External wall details | A3 | 1:10 | Pending
2577-SK-XX-DR-A-52101 | Internal wall details | A3 | 1:10 | Pending
52700 | ROOF DETAILS
2577-SK-16-DR-A-52700 | Roof Details | A3 | 1:10 | Pending
53200 | ASSEMBLY DETAILS
2577-SK-ZZ-DR-A-53200 | Window Sill, Jamb & head details | A3 | 1:5 | Pending
2577-SK-ZZ-DR-A-53201 | Door Jamb & head details | A3 | 1:5 | Pending
54200 | INTERNAL WALL FINISHES DETAILS
2577-SK-ZZ-DR-A-54200 | Skirting details MDF and Tile | A3 | 1:5 | Pending
57300 | SANITARY FITTINGS DETAILS
2577-SK-ZZ-DR-A-57300 | Vanity Top Details | A1 | 1:100 | Pending
|  | KEY | PENDING
PARTIAL
DONE

## TG KAWA (2)
Project Name | KAWA HOUSING DEVELOPMENT FOR TRUE GROUP
Project Number | SK/22/2577
Project Stage | STAGE 4.1 -DETAIL DESIGN
Date | 2022-06-02
Role | Company | Role
Client | TG KAWA LIMITED | M & E | BURHANI ENGINEERS
Project Manager |  | QS | TOWER COST
Architect | SYMBION
Structural Engineer | PINNACLE ENGINEERING SERVICES LIMITED
Deliverables Schedule
Sheet Number | Drawing Title | Paper size | Scale | STATUS | DURATION | START DATE | END DATE
0000 | GENERAL |  |  |  | 1 day
2577-SK-00-DR-A-0001 | Site Plan | A1 | 1:100 | Partial
1100 | SETTING OUT
2577-SK-00-DR-A-1101 | Ground Floor | A1 | 1:100 | Pending
2577-SK-01-DR-A-1102 | First Floor | A1 | 1:100 | Pending
2577-SK-02-DR-A-1103 | Typical 2nd-7th Floor | A1 | 1:100 | Pending
2577-SK-07-DR-A-1104 | Roof Terrace Level | A1 | 1:100 | Pending
2577-SK-15-DR-A-1105 | Upper Roof Level | A1 | 1:100 | Pending
1300 | OPENINGS LAYOUTS |  |  |  | 1/2 day
2577-SK-00-DR-A-1301 | Ground Floor | A1 | 1:100 | Pending
2577-SK-01-DR-A-1302 | First Floor | A1 | 1:100 | Pending
2577-SK-01-DR-A-1303 | Typical 2nd-7th Floor | A1 | 1:100 | Pending
2577-SK-01-DR-A-1304 | Roof Terrace Level | A1 | 1:100 | Pending
2000 | SECTIONS AND ELEVATIONS |  |  |  | 1/2 day
2577-SK-XX-DR-A-2001 | Elevation 01 | A1 | 1:100 | Partial
2577-SK-XX-DR-A-2002 | Elevation 02 | A1 | 1:100 | Partial
2577-SK-XX-DR-A-2003 | Elevation 03 | A1 | 1:100 | Partial
2577-SK-XX-DR-A-2004 | Elevation 04 | A1 | 1:100 | Partial
2577-SK-XX-DR-A-2100 | Section 01 | A1 | 1:100 | Partial
3000 | BLOWUPS |  |  |  | 1 day
2577-SK-XX-DR-A-3001 | Ground Floor Washroom | A1 | 1:20 | Pending
2577-SK-XX-DR-A-3002 | Standard Studio Blowup | A1 | 1:20 | Partial
2577-SK-XX-DR-A-34401 | Ground Floor Staircase | A1 | 1:20 | Pending
2577-SK-XX-DR-A-34400 | Typical Floor Staircase | A1 | 1:20 | Pending
42100 | EXTERNAL WALL SCHEDULES |  |  |  | 1/8 day
2577-SK-ZZ-DR-A-42100 | 200mm Thick Masonry Wall | A4 | 1:5 | Pending
2577-SK-ZZ-DR-A-42101 | 150mm Thick Masonry Wall | A4 | 1:5 | Pending
2577-SK-ZZ-DR-A-42102 | 100mm Thick Masonry Wall | A4 | 1:5 | Pending
43000 | DOOR & WINDOW SCHEDULES |  |  |  | 1 day
2577-SK-ZZ-SH-A-43101 | Door Schedule | A4 | 1:20 | Pending
2577-SK-ZZ-SH-A-43102 | Window Schedule | A4 | 1:20 | Pending
2577-SK-XX-SH-A-43050 | Iron Mongery schedule | A4 | NTS | Pending
44000 | FINISHES SCHEDULES |  |  |  | 1/2 day
2577-SK-ZZ-SH-A-44000 | Finishes and Specifications schedules | A4 | NTS | Pending
52100 | EXTERNAL WALL DETAILS |  |  |  | 1/2 day
2577-SK-XX-DR-A-52100 | External wall details | A3 | 1:10 | Pending
2577-SK-XX-DR-A-52101 | Internal wall details | A3 | 1:10 | Pending
52700 | ROOF DETAILS |  |  |  | 1/8 day
2577-SK-16-DR-A-52700 | Roof Details | A3 | 1:10 | Pending
53200 | ASSEMBLY DETAILS |  |  |  | 1/8 day
2577-SK-ZZ-DR-A-53200 | Window Sill, Jamb & head details | A3 | 1:5 | Pending
2577-SK-ZZ-DR-A-53201 | Door Jamb & head details | A3 | 1:5 | Pending
54200 | INTERNAL WALL FINISHES DETAILS
2577-SK-ZZ-DR-A-54200 | Skirting details Screed and Tile | A3 | 1:5 | Pending
|  | KEY | PENDING
PARTIAL
DONE

## TG SHEET
0000 | GENERAL
2577-SK-00-DR-A-0001 | Site Plan | A1 | 1:100
1100 | SETTING OUT
2577-SK-00-DR-A-1101 | Ground Floor | A1 | 1:100
2577-SK-01-DR-A-1102 | First Floor | A1 | 1:100
2577-SK-02-DR-A-1103 | Typical 2nd-7th Floor | A1 | 1:100
2577-SK-07-DR-A-1104 | Roof Terrace Level | A1 | 1:100
2577-SK-15-DR-A-1105 | Upper Roof Level | A1 | 1:100
1300 | OPENINGS LAYOUTS
2577-SK-00-DR-A-1301 | Ground Floor | A1 | 1:100
2577-SK-01-DR-A-1302 | First Floor | A1 | 1:100
2577-SK-01-DR-A-1303 | Typical 2nd-7th Floor | A1 | 1:100
2577-SK-01-DR-A-1304 | Roof Terrace Level | A1 | 1:100
2000 | SECTIONS AND ELEVATIONS
2577-SK-XX-DR-A-2001 | Elevation 01 | A1 | 1:100
2577-SK-XX-DR-A-2002 | Elevation 02 | A1 | 1:100
2577-SK-XX-DR-A-2003 | Elevation 03 | A1 | 1:100
2577-SK-XX-DR-A-2004 | Elevation 04 | A1 | 1:100
2577-SK-XX-DR-A-2100 | Section 01 | A1 | 1:100
3000 | BLOWUPS
2577-SK-XX-DR-A-3001 | Ground Floor Washroom | A1 | 1:20
2577-SK-XX-DR-A-3002 | Standard Studio Blowup | A1 | 1:20
2577-SK-XX-DR-A-34401 | Ground Floor Staircase | A1 | 1:20
2577-SK-XX-DR-A-34400 | Typical Floor Staircase | A1 | 1:20
42100 | EXTERNAL WALL SCHEDULES
2577-SK-ZZ-DR-A-42100 | 200mm Thick Masonry Wall | A4 | 1:5
2577-SK-ZZ-DR-A-42101 | 150mm Thick Masonry Wall | A4 | 1:5
2577-SK-ZZ-DR-A-42102 | 100mm Thick Masonry Wall | A4 | 1:5
43000 | DOOR & WINDOW SCHEDULES
2577-SK-ZZ-SH-A-43101 | Door Schedule | A4 | 1:20
2577-SK-ZZ-SH-A-43102 | Window Schedule | A4 | 1:20
2577-SK-XX-SH-A-43050 | Iron Mongery schedule | A4 | NTS
44000 | FINISHES SCHEDULES
2577-SK-ZZ-SH-A-44000 | Finishes and Specifications schedules | A4 | NTS
52100 | EXTERNAL WALL DETAILS
2577-SK-XX-DR-A-52100 | External wall details | A3 | 1:10
2577-SK-XX-DR-A-52101 | Internal wall details | A3 | 1:10
52700 | ROOF DETAILS
2577-SK-16-DR-A-52700 | Roof Details | A3 | 1:10
53200 | ASSEMBLY DETAILS
2577-SK-ZZ-DR-A-53200 | Window Sill, Jamb & head details | A3 | 1:5
2577-SK-ZZ-DR-A-53201 | Door Jamb & head details | A3 | 1:5
54200 | INTERNAL WALL FINISHES DETAILS
2577-SK-ZZ-DR-A-54200 | Skirting details Screed and Tile | A3 | 1:5